Maryland Transformation Project Update.

August 26, 2024

Applications received:

Creative Options

- Interested in increasing CIE and CLE with belief that people benefit from both.  Organization serves people with dual diagnosis.

- Exec has been with organization for 30 years but has excellent values and recognizes that changes need to be made

- Suggested that next meeting include the Day and Employment Manager (CESP) and a new staff person (is taking ACRE) who works with them primarily for behavioral supports.  Also asked them to identify 1-2 individuals that we can track and follow while introducing new processes.

Update

- CEO did not contact me after the first conversation, (Beth Eaby?)

Abilities Network

- Met with program manager, Allan Sheehan.  He is interested in expanding employment.  Sent several resources to him and we have another meeting scheduled for September 5 to be attended by additional staff.

St. Coletta

- Met with the job developer.  Interest in knowing more about effective job development and Discovery practices.  The are using the personal profile form but documenting what they are learning based on what the person is doing within the building.  The job developer understands that discovery needs to take place in the community and will try to do this with one or two people before our next call. Laura Staul

Update

- Scheduled for last week but job developer asked to reschedule and waiting to hear for next available date.

Harford Center

- Met with Dave Black the Executive Director who is committed to “supported employment”.  When we met prior to July 4th, he said that he would contact me when his employment staff return from vacations so that the next discussion will be with the entire team.  Our next meeting has not been scheduled.

Update

- He has not contacted me to reschedule.

Standard Integrated Supports

- Initial technical assistance call scheduled for 9/5

Arc of Carroll County

- Employment Initiative will be launched September 1 (Employment Pioneers)

- Staff had conversation with SEEC and will visit with their job placement staff to learn more about employer engagement.

- Created new job descriptions and reallocated duties of several new staff

Complete Care Support Services

- Had initial conversation with Program Manager.  They are looking for TA regarding employment and CLE.  Will need to coordinate with our CLE staff on setting up TA call.  They are also interested in learning how to involve individuals in community services during the winter when there are fewer opportunities.

- They will discuss and determine suitable dates/times for monthly technical assistance calls.

- They will consider which staff members to include in future technical assistance calls.

No response to email requesting introduction call:

First Choice Care

SEEC

Charity Hearts